## LOGIN PAGE
KERALAPSC
VERSION NO:WINDOWS 10 |  |  |  | DATE:17/1/23
VERIFIED BY:RAKHY |  |  |  | TESTED BY:RESMA DINESH
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
PSC_LP_01 | check whether when we click on one time registration link is open. | 1. open keralapsc. 2.click on one time registration. | www.keralapsc.gov.in | should open one time registration login. | same as expected | pass
PSC_LP_02 | check whether we can keep all textbox unfilled. | 1.click on one time registration. 2.keep all textbox empty. | www.keralapsc.gov.in | should show an error message that all field are required. | same as expected | pass
PSC_LP_03 | check whether we can login by filling correct userid and password. | 1.click on one time registration 2.enter userid and password | www.kersalapsc.gov.in | should be able to login to the profile | same as expected | pass
PSC_LP_04 | check whether if we can enter invalid userid and valid password | 1.click on one time registration. 2.keep all textbox empty. | www.keralapsc.gov.in | should not we can login | same as expected | pass
PSC_LP_05 | check whether we can login without entering access code | 1.click on one time registration. 2.keep access code empty. | www.keralapsc.gov.in | should not be able to login since it throws an error message enter the access code as in image | same as expected | pass
PSC_LP_06 | check whether if we can login by entering wrong access code. | 1. click on one time registration. 2.filling invalid access code. | www.keralapsc.gov.in | should not be able to login since it throws an error message access code doesnot match. | The website allowed to login with invalid access code | fail
PSC_LP_07 | check whether we can login by entering valid access code | 1.click on one time registration. 2.filling valid access code | www.keralapsc.gov.in | should able to login with valid access code. | same as expected | pass
PSC_LP_08 | check whether we can reset password by filling all valid datas. | 1.click on one time registration. 2.filling valid datas. | www.keralapsc.gov.in | should be able to create a new password | same as expected | pass | 0
PSC_LP_09 | check whether we can enter date of birth inDD/MM/YYYY format. | 1. click on one time registration. 2.click on forgot password. 3.enter date of birth | www.keralapsc.gov.in | should be able to create new password. | same as expected | pass
PSC_LP_10 | check whether we can enter date of birth inyyyy/mm/dd format | 1.click on one time registration. 2.click on forgot password. 3.enter 1991/3/1. | www.keralapsc.gov.in | should not be able to enter since the format is wrong | same as expected | pass
PSC_LP_11 | check whether we can give id prof as pancard | 1.click on one time registration. 2.click on forgot password. 3.select radio button | www.keralapsc.gov.in | should be able to create new password. | same as expected | pass
PSC_LP_12 | check whether we can select capcha | 1.click on one time registratin. 2.click on forgot password. 3.enter given capcha. | www.keralapsc.gov.in | should be able to create a new password. | same as expected | pass
PSC_LP_13 | check whether we can click reset button. | 1.click on forgot password. 2.click reset button. | www.keralapsc.gov.in | should be able to create new password. | same as expected. | pass
PSC_LP_14 | check whether we can select close button. | 1.click on forgot password. 2.click close button. | www.keralapsc.gov.in | should not be able to create new password. | same as expected | pass
PSC_LP_15 | check whether on clicking resize photograph/signature we can do it or not. | 1.click resize photograph/signature. 2.upload file for signature and photograph. | www.keralapsc.gov.in | should be able to upload photograph and signature. | same as expected | pass
PSC_LP_16 | check whether on clicking bulletin subscription we can select individual subscription/agency subscription and select proceed. | 1.click on bulletin subscription. 2.select individual subscripber/agency subscriber. 3.select proceed. | www.keralapsc.gov.in | should be able to get psc bulletin subscription. | same as expected | pass
PSC_LP_17 | check whether on clicking bulletin subscription we can select cancel. | 1.click on bulletin subscription. 2.click on cancel | www.keralapsc.gov.in | should not get bulletin subscription | same as expected | pass
PSC_LP_18 | check whether on clicking frequently asked questions we can clear our doubts | 1.click on frequently asked questions | www.keralapsc.gov.in | should clear all doubts | same as expected | pass
PSC_LP_19 | check whether on clicking sms options it is available | click on sms options available | www.keralapsc.gov.in | should be able to do sms to know userid and to reset password. | same as exprected | pass
PSC_LP_20 | check whether we can make a call to given numbers in working hours. | take the landline numbers and make a call | www.keralapsc.gov.in | should be able to make a call | unable to make a call | fail
PSC_LP_21 | check whether the webpage is visible in all browsers | check in all browsers | www.keralapsc.gov.in | should able to see in all browsers | unable to see | fail
PSC_LP_22 | check whether the colours used are soothing to the eyes | check colourscombinations | www.keralapsc.gov.in | all the colour combination are soothing to the eyes | colour combinations are not good to the eyes | fail
PSC_LP_23 | check multiple users are allowed to use the website | try to login repeatedly | www.keralapsc.gov.in | multiple users should be allowed | multiple users are not allowed | fail
PSC_LP_24 | check whether maps are available | try to open given map | www.keralapsc.gov.in | maps should be correctly placed | maps are not centralily placed and highlighted | fail

## REGISTRATION PAGE
KERALAPSC
VERSION NO:WINDOWS 10 |  |  |  | DATE:17/1/2023
VERIFIED BY:RAKHY |  |  |  | TESTED BY:RESMA DINESH
REGISTRATION PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
PSC_RP_01 | check whether when we click one time registration new registration link is open. | 1. open kpsc thulasi. 2.click one time registration. 3.click new registration. | www.kpsc.gov.in | should open the registration page. | new registration is open | pass
PSC_RP_02 | check all text boxes and radio buttons are selectable and can be filled | 1.click new registration 2.select radiobuttons and textboxes | www.kpsc.gov.in | should select radiobuttons and fill textboxes | same as expected | pass
PSC_RP_03 | check whether we can register without filling userid and password | 1.click new registration . 2.keep userid and password blank | www.kpsc.gov.in | should not be able to create a new registration since it shows an error message | same as expected | pass
PSC_RP_04 | check whether we can give alphanumeric values in phone no | 1.click new registration. 2.type 45678hggfgh | www.kpsc.gov.in | should not be able to register since it shows an error message | same as expected | pass
PSC_RP_05 | check whether we can give less than 10 digits in phone no | 1.click new registration. 2.type23456 | www.kpsc.gov.in | should not be able to register since it shows an error message that it is invalid | same as expected | pass
PSC_RP_06 | check whether we can give more than 10 digits | 1.click new registeration. 2.type 123456678900 | www.kpsc.gov.in | should not able to register since it shows an error message that it is invalid | same as expected | pass
PSC_RP_07 | check whether we can enter password less than minimum | 1.click new registration. 2.type 123a | www.kpsc.gov.in | should not be able to register since it shows an error message fields doesnot match | same as expected | pass
PSC_RP_08 | check whether we can enter password greater thann maximum | 1.click new registration. 2.type 12345jhghg | www.kpsc.gov.in | should not be able to register since it shows an error message fields doesnot match. | same as expected | pass
PSC_RP_09 | verify date between 1-31 | 1.click on new registration . 2. type 2-1-1991 | www.kpsc.gov.in | should be able to register | same as expected | pass
PSC_RP_10 | verify month between 1-12 | 1.click new registration. 2.type 1-2-1992 | www.kpsc.gov.in | should be able to register | same as expected | pass
PSC_RP_11 | verify year as 4 digit | 1.click new registration. 2.2-2-2002 | www.kpsc.gov.in | should be able to register | same as expected | pass
PSC_RP_12 | check whether we can enter day as 32 in dob field | 1.click new registration. 2.32-1-1991 | www.kpsc.gov.in | should not register since it shows an error message invalid data | same as expected | pass
PSC_RP_13 | verify that required /mandatory field are marked with *argument | 1.click new registration 2.check the presence of * symbol | www.kpsc.gov.in | should be able to register | same as expected | pass
PSC_RP_14 | check whether for better user interface dropdowns/radiobuttons and checkboxes etc fields are displayed whereever possibe instead of just textboxes | 1.click new registration. 2.check each field | www.kpsc.gov.in | should able to register since all are displayed properly | same as expected | pass
PSC_RP_15 | verify the checkbox is unselected by default | 1.click new registration. 2.checkbox is not selected | www.kpsc.gov.in | should not be able to register since it shows an error message the checkbox is required | same as expected | pass
PSC_RP_16 | verify the password is in encrypted format | 1.click new registration 2.type the password and check | www.kpsc.gov.in | should be able to register | same as expected | pass
PSC_RP_17 | check whether when the user clicks on the namefield the text cursor should be visible | 1.click new registraton 2.go to name field and click on it. | www.kpsc.gov.in | should be able to register | same as expected | pass
PSC_RP_18 | check whether the user can enter numbers in the name field | click new registration. 2.type 123456 | www.kpsc.gov.in | should not be able to register since it shows an error message that we can use letters,spaces,hyphen only | same as expected | pass
PSC_RP_19 | verify new accesscode is generated in case if the user writes wrong accesscode | 1.click new registration 2.type fdhjd6 | www.kpsc.gov.in | should able to register since new accesscode is generated | sanme as expected | pass
PSC_RP_20 | check whether when we click on register registrationis done | click register | www.kpsc.gov.in | should be able to register | same as expected | pass
PSC_RP_21 | check whether the page is found | press the back key | www.kpsc.gov.in | should find the webpage | should not find the webpage | fail
PSC_RP_22 | check whether the font size is correct | try to read the words that are readable | www.kpsc.gov.in | should be able to read the text | cannot read the words | fail
PSC_RP_23 | check whether the registration page is overloaded . | try to find every details eazily | www.kpsc.gov.in | should be able to find details eazily | cannot find details eazily | fail
PSC_RP_24 | check whether we can load old website | click on load old website | www.kpsc.gov.in | should be able to load old website | cannot load old website | fail
PSC_RP_25 | check whether there is internet connection at the time of registration | click on register button | www.kpsc.gov.in | should be able to register | cannot register it shows resubmission error | fail
PSC_RP_26 | check if the site could be reached | click on register button | www.kpsc.gov.in | should be able to register | cannot register it shows site cannot be reached | fail

## TEST REPORT
TEST REPORT
SL NO | MODULE NAME | TESTCASE PASSED | TESTCASE FAILED | TOTAL TESTCASE
1 | LOGIN PAGE | 18 | 6 | 24
2 | REGISTRATION PAGE | 20 | 6 | 26

## BUGREPORT
KERALAPSC
VERSION NO:WINDOWS 10 |  |  |  | DATE:18/1/2023
VERIFIED BY:RAKHY |  |  |  | TESTED BY:RESMADINESH
BUGID | TESTID | EXPECTED RESULT | BUG | STEPS FOR REPRODUCE | SEVERITY | PRIORITY | SCREENSHOT | STATUS
DEF_PSC_01 | PSC_RP_21 | webpage found and looks like everything found in this location | page not found | 1.open www.kpsc.gov.in 2.click on webpage | critical |  |  | new
DEF_PSC_02 | PSC_LP_26 | website should be visible in all browsers | website is viewed only in firefox and google chrome | 1.open www.kpsc.gov.in 2.try to open in all browsers | minor |  |  | new
DEF_PSC_03 | PSC_LP_06 | access code match | accesscode doesnot match | 1.open www.kpsc.gov.in 2.try to login | major |  |  | new
DEF_PSC_04 | PSC_LP_22 | colous used are soothing to the eyes | too many contrasting colours,poor colour combination can harm user's eyes | 1.open www.kpsc.gov.in 2.try to see he colours used | minor |  |  | new
DEF_PSC_05 | PSC_RP_22 | font correct In size | too large or small fonts distract users | 1.open www.kpsc..gov.in 2.try to read the words if the font size is correct or not | minor |  |  | new
DEF_PSC_06 | PSC_LP_15 | photos could be uploaded eazily | psc photo upload error | 1.open www.kpsc.gov.in 2.try to upload photo | critical |  |  | new
DEF_PSC_07 | psc_lp_23 | multiple users will be allowed to use website | multiple users not allowed | 1.open www.kpsc.gov.in 2.try to login | critical |  |  | new
DEF_PSC_08 | PSC_LP_24 | the maps are at the correct position | the maps has been moved to side bar which is pretty unusual and the fonts doesnot match the design | 1.open www.kpsc.gov.in 2.try to open maps | minor |  |  | new
DEF_PSC_09 | PSC_RP_23 | the main page is not overloaded | the main page is overloaded with information and doesnot have a clear structure | 1.open www.kpsc.gov.in 2.try to see everything in main page | minor |  |  | new
DEF_PSC_10 | PSC_RP_24 | old website is active | old website is is temporarily shut down.go back to home page | 1.open www.kpsc.gov.in 2.try to open old website | critical |  |  | new
DEF_PSC_11 | PSC_RP_25 | we can submit the application | conform form resubmission error | 1.open www.kpsc.gov.in 2.check internet connection 3.submit | critical |  |  | new
DEF_PSC_12 | PSC_RP_26 | good internet connection | this site cannot be reached | 1.open website 2.try to login | critical |  |  | new

## DEFECT DISTRIBUTION GRAPH
MODULE NAME | DEFECT DISTRIBUTION
REGISTRATION PAGE | 6
LOGIN PAGE | 6